## >$200
Projects in Progress - over $200,000 | JCOS Approval Req'd Approved | Original Budget | Revised Project Budget | Actual Expenditures to Date | Forecast of Final Cost | Source of Funding
University Student Housing | Yes 10/17/2000 | 21000000 | 21000000 | 20855686 | 21000000 | 2001 Bond Issue
Fund Number 70514,70608,70609
Status: Construction Punch List which should be closed by May 2006
Board of Trustees Approved: March 2000
Projected Completion Date: May 2006
Comment: Landscape Improvements in progress - 95%
Energy Service Project | Yes 12/1/2005 | 11868188 | 11868188 | 2014492 | 11868188 | Existing debt service and projected energy
Fund Number: 70625 | [5 empty] | savings
Status: Work In Progress
Board of Trustees Approved: October 2005
Projected Completion Date: November 2007
Comment: Project in Design Engineering Phase
Meadow Brook Hall Repairs/Renovation Project | Yes 06/17/2005 | 7000000 | 7000000 | 2020172.87 | 7000000 | Matilda R. Wilson Fund Charitable Trust
Fund Number 70589
Status: Construction - 34%
Board of Trustees Approved: June 2004
Projected Completion Date: February 2007
HTHW Trench & Piping Project | Yes 12/01/2005 | 5800000 | 5800000 | 0 | 5800000 | Existing debt service and projected energy
Fund Number: 70624 | [5 empty] | savings
Status: Engineering Phase
Board of Trustees Approved: October 2005
Projected Completion Date: February 2007
Comment: Engineering RFP awarded December 2005
Vandenberg Hall Dining Renovation | Yes 04/21/2005 | 1500000 | 1571000 | 1564894.3 | 1571000 | $ 1.3M - Chartwell Funding
Fund Number: 70612 | [5 empty] | $ 200,000 - #45489 Vandenberg Hall Reserves
Status: Waiting on final invoices | [5 empty] | $ 71,000 - #45489 Vandenbeurg Hall Reserves
Board of Trustees Approved: April 2005
Projected Completion Date: February 2006
Comment: $1.3M of funds from Food Vendor
Comment: $200,000 of funds from Department
Comment: $71,000 need for abatement issues added to project, Revised Use and Finance Statement approved | Yes 09/29/2005
South Foundation Hall Classroom Improvements | No | 481000 | 521000 | 500941.69 | 521000 | $131,000 - #14484 FY04 Year-End Funds
Fund Number 70592 | [5 empty] | $350,000 - #14407 Academic Affairs Funds
Status: Waiting on last invoices | [5 empty] | $ 40,000 - #14292 Strategic Plan Fund
Board of Trustees Approved: July 2004
Projected Completion Date: February 2006
Comment: Additional technology added
Golf Course Bridge Replacement | No | 20000 | 350000 | 311077 | 324000 | $ 85,000 - #20921 Insurance Settlement
Fund Number 70587,70209 | [5 empty] | $ 49,000 - #20921 Insurance Reserve
Status: To be closed in February 2006 | [5 empty] | $189,000 - #24350 Capital Projects Supplement Fd
Board of Trustees Approved: April 2005 | [5 empty] | $ 1,000 - #70209 Golf Course Deductible
Project Completion Date: February 2006
Comment: Waiting on last invoice before closing
OC Gold Room Renovation | No | 190000 | 245092 | 110195.42 | 245092 | $190,000 - #70211 Oakland Center Reserves
Fund Number 70619 | [5 empty] | $ 8,000 - #70211 Oakland Center Reserves
Status: Construction 80% | [5 empty] | $ 47,092 - #70211 Oakland Center Reserves
Board of Trustees Approved: June 2005
Project Completion Date: April 2006
Comment: Increase $8,000 due to actual bids
Comment: Increase $47,092 due to additional asbestos work above the ceiling
Dodge Hall Cooling System | No | 25000 | 226724 | 15597.2 | 226724 | $200,000 - #14685 FY05 Year-End Funds
Fund Number 70604 | [5 empty] | $ 26,724 - #19542 UTS Electronic Sys Oper
Status: Out for bids
Board of Trustees Approved: October 2005
Project Completion Date: September 2006
Comment: Increase $201,724 result of definition determined in design
TOTAL PROJECTS IN PROGRESS |  | 47859188 | 48355280 | 27377459.28 | 48329280
Notes:
1. Revised Project Budget equals the Original Budget plus all approved changes to the budget.
2. Projects are added to the report when a funding source has been identified and a plant fund account authorized for the project.
3. The project status will be reported as "Completed" when the "actual expenditures to date" equals the "forecast", TMA work
order system ties to Banner, and no additional expenditures or work is anticipated on the project.
4. A project whose status has been reported as complete to the Board, will be removed from the report for the next Board meeting.