## >$200
Projects in Progress - over $200,000 | JCOS Approval Required |  | Original Budget | Revised Project Budget | Actual Expenditures to Date | Forecast of Final Cost | Source of Funding | Proj Mgr
University Student Housing | Yes | 2000-10-17 | 21000000 | 21000000 | 20922754.78 | 21000000 | 2001 Bond Issue | Janet
Fund Number 70514,70608,70638
Status: Construction Punch List, waiting on invoices
Board of Trustees Approved: March 2000
Projected Completion Date: June 2007
Comment: Landscape Improvements in progress - waiting on warranty work and final invoices
Energy Service Project | Yes | 2005-12-01 | 11868188 | 11868188 | 5945279 | 11868188 | Existing debt service and projected energy | Janet
Fund Number: 70625 | [6 empty] | savings
Status: Work In Progress
Board of Trustees Approved: October 2005
Projected Completion Date: November 2007
Comment: Construction Phase
Meadow Brook Hall Repairs/Renovation Project / MBH Tent & Outbuilding | Yes | 2005-06-17 | 8400000 | 7055268 | 6305761 | 7055268 | $7.0M - Matilda R. Wilson Fund Charitable Trust | Janet
Fund Number 70589,70590 | [6 empty] | $24,000 - Motor Cities Nat'l Heritage Grant
Status: Construction - 99% | [6 empty] | $31,268 - MBH Reserve Fund
Board of Trustees Approved: June 2004
Projected Completion Date: June 2007
Comment: MBH Tent & Outbuilding work canceled $1.4M
Comment: Increase $55,268 due to additional grants for gutter & arbors
HTHW Trench & Piping Project | Yes | 2005-12-01 | 5800000 | 5800000 | 1773224.83 | 5800000 | Existing debt service and projected energy | Janet/Steve
Fund Number: 70624 | [6 empty] | savings
Status: Construction - 30%
Board of Trustees Approved: October 2005
Projected Completion Date: June 2007
Comment: Construction Phase
South Foundation Hall Classroom Improvements Second Floor | No |  | 865000 | 865000 | 604347.61 | 865000 | $844,800 - #14488 Year End Funds | Steve
Fund Number 70640 | [6 empty] | $ 20,200 - #12147 University Technology Fund
Status: Classroom renovation approximately 98% complete, preliminary elevator work approx. 75%
Board of Trustees Approved: March 2006
Projected Completion Date: October 2007
Comment: Elevator work to occur in summer 2007
P-3 Parking Lot Refurbishing & Expansion | No |  | 43500 | 800000 | 24978.73 | 800000 | $800,000 - #24349 Parking Improvement Reserve | Janet/Steve
Fund Number: 70653
Status: Awarded, construction to start in May 2007
Board of Trustees Approved: November 2006
Projected Completion Date: October 2007
Comments: Original budget engineering only, revised budget reflects entire project
Hamlin Hall Refurbishing | No |  | 626500 | 626500 | 539433.43 | 626500 | $626,500 - #45489 Residence Halls Rooms | Deb Wade
Fund Number 70642
Status: Construction Punch List, waiting on invoices
Board of Trustees Approved: June 2006
Projected Completion Date: April 2007
Kresge Library Exterior Wall | No |  | 160000 | 585000 | 23010.76 | 585000 | $160,000 - #24810 Plant Renewal Fund
Fund Number 70593 | [6 empty] | $290,000 - #24810 Plant Renewal Fund '07
Status: Construction to Start May 2007 | [6 empty] | $135,000 - #24810 Plant Renewal Fund '08
Board of Trustees Approved: November 2006
Project Completion Date: December 2007
Comments: Increase due to further clarity of scope
Back-Up Generator - Phase 2 | No |  | 500000 | 500000 | 188040 | 500000 | $430,000 - #24810 Plant Renewal Fund '07
Fund Number 70664 | [6 empty] | $ 70,000 - #24810 Plant Renewal Fund '08
Status: Engineering Phase; Equipment Ordered
Board of Trustees Approved: November 2006
Project Completion Date: December 2007
Underground HTHW Piping Replacement | No |  | 426900 | 426900 | 426799 | 426900 | $426,900 - #24350 Capital Project Supplement Fund | Grover
Fund Number 70654
Status: Construction completed, need to make change orders adjustments and waiting on invoices
Board of Trustees Approved: October 2006
Projected Completion Date: April 2007
OC Gold Room Renovation | No |  | 190000 | 237092 | 233236.37 | 237092 | $190,000 - #70211 Oakland Center Reserves | Stuart
Fund Number 70619 | [6 empty] | $ 8,000 - #45379 Oakland Center Operations
Status: Construction Punch List, waiting on invoices | [6 empty] | $ 39,092 - #45379 Oakland Center Operations
Board of Trustees Approved: June 2005
Project Completion Date: March 2007
Comment: Increase $8,000 due to actual bids
Comment: Increase $39,092 due to additional asbestos work above the ceiling
Dodge Hall Cooling System | No |  | 25000 | 295700 | 139996.91 | 295700 | $200,000 - #14685 FY05 Year-End Funds | Stuart
Fund Number 70604 | [6 empty] | $ 26,724 - #19542 UTS Electronic Sys Oper
Status: Construction on hold until next cooling season | [6 empty] | $ 68,976 - #19542 UTS Electronic Sys Oper | Steve
Board of Trustees Approved: March 2006
Project Completion Date: July 2007
Comment: Increase $270,700 result of definition determined in design and actual bids
Automotive Antenna Instrumentation | No |  | 220000 | 220000 | 14415 | 220000 | $220,000 - #21758 School of Engineering Special
Fund Number 70645 | [6 empty] | Research Support
Status: Waiting on material delivery; work to start in April 2007
Board of Trustees Approved: June 2006
Projected Completion Date: June 2007
TOTAL PROJECTS IN PROGRESS |  |  | 50125088 | 50279648 | 37141277.42 | 50279648
Notes:
1. Revised Project Budget equals the Original Budget plus all approved changes to the budget.
2. Projects are added to the report when a funding source has been identified and a plant fund is authorized for the project.
3. The project status will be reported as "Completed" when the "actual expenditures to date" equals the "forecast", TMA work
order system ties to Banner, and no additional expenditures or work is anticipated on the project.
4. A project whose status has been reported as complete to the Board, will be removed from the report for the next Board meeting.