## Project Info (hidden)
|  |  |  | SmithGroup |  | Descriptions | Remarks | Linked Cell Names | Linked Cells
PROJECT INFORMATION | [5 empty] | Estimate Stage |  | Estimate Stage | Concept
Conceptual Study
| Project Name 1 | Oakland University | Lead Estimator |  |  | Schematic Design
| Project Name 2 | Meadow Brook Hall Renovations | Estimator 1 |  |  | Design Development
| Project City, State | Rochester, Michigan | Estimator 2 (Elect) |  |  | Construction Document
Estimator 3 (Mech)
| Project Number | 21868 | Estimator 4
[6 empty] | Estimate Type | Used for : | Estimate Type | Parametric Budget
| Estimate Stage |  | REPORT INFORMATION |  |  | Cost Study | Conceptual Budget
| Estimate Type |  |  |  |  | Cost Model | Conceptual Budget
| Report Date | 2003-11-26 | Section 1 | A. Exterior - Wood Half-timbers | ARCH | Cost Plan | Conceptual/SD/DD
|  |  | Section 2 | B. Exterior - Parapets, Copings and Stonework |  | Cost Check | DD/CD
| Bid Date | 2003-11-26 | Section 3 | C. Exterior - Roof |  | Cost Estimate | 90% CD/Pre Bid Estimate
| Construction Period | 24 | Section 4 | D. Exterior - Foundation & Structural Repairs
|  |  | Section 5 | E. Exterior - Gutters
| Client Contact Name | Kevin Shultis | Section 6 | F. Exterior - Chimneys
| Client Company Name | SmithGroup | Section 7 | G. Exterior - Doors |  | Estimating Team Member | Initial | Lead Estimator | Jack Edwartoski, PE | Director of Facility Economics
| Client Address 1 | 500 Griswold, Suite 200 | Section 8 | H. Exterior - Windows |  | Alistair Law | AL | Estimator 1
| Client Address 2 |  | Section 9 | I. Exterior - Limestone around windows |  | Consultant | Con | Estimator 2
| Client City | Detroit | Section 10 | J. Exterior - Knoll Cottage |  | Frank Fields | FF | Estimator 3
| Client State | MI | Section 11 | K. Exterior - Bridge |  | Jack Edwartosky | JE | Estimator 4
| Client Zip | 48226 | Section 12 | L. Interior - Carved Plaster Ceiling |  | Jehana Jalil | JJ
| Client Country | USA | Section 13 | M. Interior - Plaster Walls |  | Jenny Young | JY
| Client Phone | (313) 442-8318 | Section 14 | N. Interior - Stone Floors |  | John Murray | JM
| Client Fax | 313442817 | Section 15 | O. Interior - Tile Work |  | John Simpson | JS
| Client E-mail | Kevin.Shultis@smithgroup.com | Section 16 | Pa. Knoll Cottage |  | Jonathan Moss | JTM
|  |  | Section 17 | A. Wilson Room | ROOM RENOVATIONS | Ken Pang | KP
|  |  | Section 18 | B. Lower Level: Expand 3 Ex. Restrooms |  | Salam Farjo | SF
|  |  | Section 19 | C. Lower Level: New Restroom |  | Kevin Oliveira | KO
|  |  | Section 20 | D. Floral Room. |  | Glascock & Garnes | G&G
|  |  | Section 21 | E. Carriage House, Loft, Garage |  | Khalid Suhail | KS
|  |  | Section 22 | F. Floor Protection
|  |  | Section 23 | G. Stanchions, Signs
|  |  | Section 24 | H. Kitchen Refrigerators
|  |  | Section 25 | I. Restroom for Tents
|  |  | Section 26 | J. Kitchen for Tents
|  |  | Section 27 | K. Kitchen Upgrades
|  |  | Section 28 | L. New Second Tent off Sun Porch
|  |  | Section 29 | M. Pad for Tent off Sun Porch
|  |  | Section 54 | N. Upgrade Existing Tend
|  |  | Section 55 | O. Replace Existing Tent
|  |  | Section 56 | P.
Section 57
|  |  | Section 58 | Q. Room Renovations
|  |  | Section 59 | I. Fire Protection - Kitchen Equipment System
|  |  | Section 60 | J. Rose Garden
|  |  | Section 61 | E. Knoll Cottage
|  |  | Section 62 | F. Carriage House
|  |  | Section 63 | G. Wilson Room
|  |  | Section 64 | I. Convert Steam to Hot Water
|  |  | Section 65 | J. Plumbing Fixtures
|  |  | Section 66 | S. Basement Level
|  |  | Section 67 | T. First Level
|  |  | Section 68 | U. Second Level
|  |  | Section 69 | V. Third Level
|  |  | Section 70 | W. Waterproofing
|  |  | Section 72 | R. Draperies & Fabric Wall Coverings
|  |  | Section 30 | A. Plumbing - New HW Heater | MECH
|  |  | Section 31 | B. Mechanical - Update Steam Distribution System
|  |  | Section 32 | C. HVAC - Climate Control, Ground & 1st Floors
|  |  | Section 33 | D. HVAC - Climate Control 2nd & 3rd Floors
|  |  | Section 34 | E. HVAC - Controls
|  |  | Section 35 | F. Refrigeration - Liquor Control Room
|  |  | Section 36 | Ga. HVAC - Knoll Cottage
|  |  | Section 37 | H. Fire Protection - Building Systems
|  |  | Section 71 | Gb. HVAC - Wilson Room & Carriage House | ELECT
|  |  | Section 39 | A. Electrical - Upgrades & Repairs
|  |  | Section 40 | B. Electrical - Lighting & Controls
|  |  | Section 41 | C. Electrical - Emergency Generator
|  |  | Section 42 | D. Electrical - Security System
|  |  | Section 43 | E. Fire Protection System
|  |  | Section 44 | A. Grounds - Stone Walk | GROUNDS
|  |  | Section 45 | B. Grounds - Pegasus Fountain
|  |  | Section 46 | C. Grounds - Gazebo Fountain
|  |  | Section 47 | D. Grounds - Gazebo Steps
|  |  | Section 48 | E. Grounds - Gazebo Interior
|  |  | Section 49 | F. Grounds - Woodland Entrance
|  |  | Section 50 | G. Grounds - Parking Lots
|  |  | Section 51 | H. Grounds - Equipment Purchase
|  |  | Section 52 | I. Tent Pad - Replace Asphalt Paving
|  |  | Section 73 | Pb. Garage
|  |  | Section 74 | Pc. Carriage House
|  |  | Section 75 | Pd. Subgrade Utility Under Courtyard
|  |  | Section 76 | AA.
|  |  | Section 77 | BB.
|  |  | Section 53 | #REF!

## Cover (hidden)
2003-11-26
Kevin Shultis
SmithGroup
500 Griswold, Suite 200
Detroit, MI 48226
Oakland University
Meadow Brook Hall Renovations
Rochester, Michigan
Dear Kevin,
We enclose herewith our recommended Concept Parametric Budget for the project mentioned above.
#REF!
This estimate incorporates the following areas:
Architectural Changes A through Q
Mechanical Changes A through I
Electrical Changes A and D
Grounds Changes A and J
We would be pleased to discuss these costs further with you at your convenience.
Sincerely,
Jack Edwartoski, PE
Director of Facility Economics
Enclosures
21868

## Basis (hidden)
Oakland University |  |  |  | SmithGroup
Meadow Brook Hall Renovations |  |  | 2003-11-26 |  | 37951
Rochester, Michigan
BASIS OF COST ESTIMATE
The following documentation was used in preparation of this Budget Cost Estimate:
Floor Plans dated 1-22-73
Site Walk-around
Discussions with Facilities Staff
Discussions with SG Project Architects and Engineers.
The pricing is based on the following general conditions of construction:
This work to be done concurrent with the base project scope.
Construction duration of 24 months should be included as a part of this change.
The work required by this Project will be cooordinated and facilitated by a Construction Manager, separately contracted to Oakland University.
The contractor will be required to pay prevailing wages
Where possible, pricing parameters are spelled-out in the "Breakdown" sections of the estimate backup. When necessary, Lump Sum Allowances are used and will be in those sections too.
#REF!
This estimate has been based on a closed bid situation with a limited number of general and sub contractors performing the work. Experience indicates that the fewer number of bidders will result in higher bids compared to new work..

## Estimate Summary
Oakland University | [5 empty] | SmithGroup
Meadow Brook Hall Renovations | [5 empty] | 2003-12-04
Rochester, Michigan
CONSTRUCTION COST SUMMARY |  |  | Budget | Budget | Recommend | Total Budget
|  |  | Short Term Needs | Long Term Needs
A. Construction:
| Architectural: |  |  |  |  | 6277969.6964
| A. Exterior - Wood Half-timbers |  | 42635
| B. Exterior - Brick Parapets, Copings, Stonework & Chimneys |  | 52322.3214
| C. Exterior - Roof |  | 180000
| D. Exterior - Foundation & Structural Repairs |  | 30630
| E. Exterior - Gutters |  | 26171.875
| F. Exterior - Chimneys (included in Item B above) |  | 0
| G. Exterior - Doors |  | 36462.5
| H. Exterior - Windows |  | 315898
| I. Exterior - Limestone around windows |  | 24000
| J. Exterior - Knoll Cottage (incl. In Item Ta. Below) |  | 0
| K. Exterior - Bridge |  | 19000
| L. Interior - Carved Plaster Ceiling |  | 44237
| M. Interior - Plaster Walls and Ceilings |  | 49234
| N. Interior - Stone Floors |  | 16774
| O. Interior - Tile Work |  | 11525
| P. Basement Level |  |  | 590762
| Q. First Level |  |  | 337102
| R. Second Level |  |  | 380639
| S. Third Level |  |  | 80683
| Ta. Knoll Cottage |  | 25200 | 8205
| Tb. Garage |  |  | 22950
| Tc. Carriage House |  |  | 10800
| Td. Subgrade Utility Under Courtyard |  | 32500
| Ua. Room Renovations |  |  | 3227000
| Ub. Architectural allowance for condensate piping replacement |  | 224239
| V. Draperies & Fabric Wall Coverings |  |  | 75000
| W. Waterproofing |  | 139000
X. Art, Furnishings and Antiques Conservation
| Y. Repair/Rehab/Update Restrooms |  | 275000
| Architectural Subtotal |  | 1544828.6964 | 4733141
| Mechanical: |  |  |  |  | 1852614
| A. Plumbing - New HW Heater |  | 0
| B. New Boiler Feed |  | 20000
| C. Replace Boilers |  |  | 280000
| D. Mechanical - Replace/Repair Condensate Piping |  | 220000 | 180000
| E. Mechanical - Update Steam Distribution System |  | 238000
| F. HVAC - Refurbish Ground & 1st Floors |  | 150000
| G. HVAC - Refurbish 2nd & 3rd Floors |  |  | 18800
| H. HVAC - Controls |  | 138000 | 442000
| I. Refrigeration - Liquor Control Room |  | 0
| J. HVAC - Knoll Cottage |  | 15972
| K. HVAC - Wilson Room & Carriage House |  | 84942
| L. Fire Protection - Kitchen Equipment System |  | 0
| M. Plumbing Fixtures |  | 20900
| N. Testing |  | 44000
| O. Impact of Mech. Work on Architectural Finishes |  | 0
(incl. In Architectural , Item Ub. )
| Mechanical Subtotal |  | 931814 | 920800
| Electrical: |  |  |  |  | 778501
| A. Electrical - Upgrades & Repairs |  | 15280
| B. Electrical - Lighting & Controls |  | 62158
| C. Electrical - Emergency Generator |  | 135000
| D. Electrical - Security System |  | 195700
| E. Electrical - Fire Alarm System |  | 333300
| F. Inspections |  | 10000
| G. Knoll Cottage |  | 15423
| H. Carriage House |  | 8825
| I. Wilson Room |  | 2815
| Electrical Subtotal |  | 778501 | 0
| Grounds: |  |  |  |  | 316352
| A. Grounds - Stone Walk |  | 26000
| B. Grounds - Pegasus Fountain |  | 28602
| C. Grounds - Gazebo Fountain |  | 10000
| D. Grounds - Gazebo Steps |  | 3000
| E. Grounds - Gazebo Interior |  | 14950
| F. Grounds - Woodland Entrance |  | 26000
| G. Grounds - Parking Lots |  | 52800
| H. Grounds - Equipment Purchase |  | 23000
| I. Tent Pad - Replace Asphalt Paving |  | 100000
| J. Rose Garden |  | 32000
| Grounds Subtotal |  | 316352 | 0
| Construction Subtotal (all items) |  | 3571495.6964 | 5653941 |  | 9225436.6964 | 9225436.6964 | Check
| Project Costs and Risk Factors |  |  |  |  | 5626031.0895
| General Conditions & Fees: 15% |  | 535724.3545 | 848091.15 | 0
| Design Contingency: 10% |  | 410722.0051 | 650203.215 | 0
| Escalation: 0% |  | 0 | 0 | 0
| Contractor's Bond: 1% |  | 45179.4206 | 71522.3537 | 0
| Bid Contingency: 5% |  | 228156.0738 | 361187.8859 | 0
| Construction Contingency: 20% |  | 958255.5101 | 1516989.1209 | 0
0
| Project Costs and Risk Factors Subtotal |  | 2178037.364 | 3447993.7255
B. Design and Review: | [5 empty] | 2079205.49
| AE & CM Fees: 14% |  | 804934.6285 | 1274270.8616 | 0
C. Mangmt. & Insp. Construction: | [5 empty] | 0
| SEE Above |  |  | 0
D. Site Acquisition: | [5 empty] | 0
| NONE |  |  | 0
E. Reservations: | [5 empty] | 0
| NONE |  |  | 0
Total Recommended Construction Cost |  |  | 6554467.6889 | 10376205.5871 | 0 | 16930673.276 | 16930673.276 | Check

## Breakdown Struc (hidden)
Proj. No.: | 21868 |  |  |  | Date: | 2003-11-26
Project Name: | #REF! |  |  |  | Classification:
Project Location: | #REF! |  |  |  | Bid Date: | 2003-11-26
Estimate Type: | #REF! |  |  |  | Gross Area SF: | N/A
ITEM |  | DESCRIPTION | QTY |  | U.P. | TOTALS
A. Exterior - Wood Half-timbers
Project Quantity |  |  | 1142.3775 | SF | 5
Change door heights (8'-10" to 7'-0") |  |  | 1142.3775 | SF | 5
Lightweight fill: 4" |  |  | 1142.3775 | SF | 5 | 5711.8875
[5 empty] | A. Exterior - Wood Half-timbers | 5711.8875

## Final Items 112603 (hidden)
| qty | unit | unit cost | total
Knole Cottage - Interior
Basement:
Rebuild brick masonry bearing under wood beam ends (2 locations @1 cu. ft. each.) | 2 | cu ft
Add wall bracket to partially support beam end (L 4x4x1/2 x 8" long; 2 epoxy anchors into brick masonry.
First Floor:
Walls:
Wash walls (1600 sf surface area distrubuted over 6 rooms) | 1600 | sf
Touch up painted wood trim (50 lf) | 50 | lf
Repair minor moderate cracks 20 lf | 20 | lf
Ceiling:
Wash ceiling 600 sf area | 600 | sf
Repair moderate cracks - 20 lf | 20 lf
Floor:
Soiled VCT - clean, reset 5 sf | 5 | sf
Windows:
Refinish clear finished oak jambs at 20 windows (1' x 2.5') | 20 | ea
Refinish painted wood jambs at 8 windows (1' x 2.5') | 8 | ea
Doors:
Refinish exterior surface of one oak door (strip, sand, clear finish) | 1 | ea
Exterior:
Steel windows: scrape, derust with wire brush (minor, scattered), prime, repaint @ 28 windows (ea 1' x 2.5') | 28 | ea
Reglaze 14 windows (new glazing compound) | 14 | ea
provide one new wood storm door (custom) | 1 | ea
Replace 20 lf of exterior painted wood trim - 1 x 4. | 20 | ea
Add soffit ventilation (custom detail); add gable vents (brick vents) | 1 | ls
New Cedar shingle roof: Remove existing cedar roof, replace damaged sheathing (assume 50 sf) with new spaced 1x boards; replace rotted rafters. treat attic for mold. Install new cedar roof over cedar breather; provide concealed ridge and soffit vents, terne coated stainless flashings. Note: Existing gutters and downspouts in vary good condition: no work except tightening up a few loose downspout joints. | 1 | ls
Site:
Adjust Drainage - regrade 100 sf to create positive drainage. Incl removal and reinstallation of 4 shrubs. | 1 | ls
Reset sand-set 2' x 2' pavers - total 100 sf
Garage:
Roof: replace back half (15' x 100') - custom clay tile. Simple roof - one side of gable roof. Salvage existing slate for reuse for repairs on house. | 1500 | sf
Exterior: 100 sf brick repointing | 100 | sf
Interior: Paint timber truss plates. | 10 | ea
Carriage House
Clean smooth interior brick walls (2000 sf area) | 2000
New interior work counter and base cabinet 15 lf
Repair leak in skylight; New lighting (utilitarian - fluorescent), Remove plywood from window interiors, selective replacement of window glazing compound. Miscellaneous repainting.
Exterior: Brick repointing - assume 100 sf | 100 | sf
Tile roof repairs: Assume selective tile replacement (assume 50 locations); detergent cleaning of roof. Flashing replacement; clean and repair gutters and downspouts (assumed scope: miscellaneous repairs to lead gutters and downspouts, including reconnecting of loose joints, cleaning out blockages) | 1 | ls
Exterior Caulking (assume 100 lf) | 100 | lf
Exterior painting (garage doors, wood trim) | 4 | ea
Subgrade utility space under Courtyard
15' x 30' area of rusted rebar in concrete ceiling - chip out conc.; remove rusted bars, add new bars, pack with non-shrink grout. | 450 sf
Find source of water penetration - possible broken pipe from domestic water. (buried underground under courtyard - conc pavers over assumed concrete slab) | 1 | ls
Room 6 - Woman's Toilet Room
General: Major update and expansion of existing Woman's bathroom. Existing bathroom 8' x 20'. New batroom to be 16' x 20.' Intent is to make restroom suitable for use at weddings and similar events. Must be accessible to disabled individuals. Level of finishes - Luxury.
Scope: gut existing rectangular 8 x 20 room, remove plbg fixtures; remove exist tile wainscot; demo 20 lf of cmu wall to provide expansion into adjacent 8' x 20' space. Selective demo of existing conc. Slab-on-grade; Re route underfloor plumbing lines, patch conc slab on grade; Provide new 8' x 16' conc floor over on steel deck over existing crawl space. New high end plumbing fixtures and accessories; undermount sinks, polished stone floors, stone countertop. Counter to ceiling mirror + 1 full length mirror. Period light fixtures. Four stalls, four lavs. Each water closet to be in a "room" with a louvered door. | 1 | ls
Room 12 - Spanish Room
Add this to the current work scope for this room:
Walls: Carefully remove damaged hand Stenciled adhered wall fabric (cut back to logical straight joint); carefully remove damaged plaster & mtl lath; Install new three coat plaster on mtl lath. (See below for new finish - hand stenciled wall cloth) | 200 | SF | 25.018 | 5003.6
New Wall Cloth with Hand Stenciling to match existing | 1 | ls |  | 12000
Room 12A
Rehabilitate 100 sf single occupancy toilet room and expand into adjacent 50 sf space to yield a very high-end bride's bathroom. Scope: Demo exist concrete slab-on-grade, Demo approx 10 lf of exist 10' high cmu walls, remove exist plumbing fixtures; New work: reroute plumbing (existing plumbing is available in the area) to new fixture locations, so underslab work must be assumed. Level of finish is to be luxury level: Assume separate "room" for water closet with louvered door. Marble wainscot, polished stone floors, marble countertops, undermount sinks, high end fixtures and accessories, high end period lighting. counter to ceiling mirror + 1 full length mirror. Facility must be accessible to disabled persons. Irregularly shaped plan, and work is adjacent to highly significant architecural spaces, so careful work will be required. | 1 | ls
Room 13 - Ballroom
Add this to the current work scope for this room:
General: Existing wood floor cannot be sanded any more, still needs protection. Size: 22' x 42'
Chemically strip, lightly hand sand, new polyurethane varnish finish | 1000 | sf
New custom woven rug. Assume woven to size 16' x 36', pile carpet, detailed repeating patern in center, border. | 575 | sf
Room 24 - Men's Toilet Room
General: Major update and expansion of existing men's bathroom, and hallway leading to it. Bathroom and hallway leading to it are currently utilitarian. Existing bathroom 8' x 23'. Intent is to make the route and restroom suitable for use at weddings and similar events. Must be accessible to disabled individuals. Level of finishes - high end. | 1 | ls
Scope:
Vestibule: Two 10' cmu walls (16 lf), with plaster finish with one custom wood rail and stile door to form vestibule with two existing walls. Single period wall sconce. | 1 | ls
Hallway:7' x 23' hallway - provide new plaster wall finish, wood wainscot, 2 custom rail and stile doors; one 4' x 10' high plaster on stud partition with 1 custom rail and stile door, new stone flooring, 4 period wall sconces. Switching. Plaster ceiling. | 1 | ls
Restroom: gut existing rectangular 8 x 23 room, remove plbg fixtures; remove exist tile wainscot; demo 15 lf of cmu wall to provide expansion into adjacent 10' x 15' space. Selective demo of existing conc. Slab-on-grade; Re route underfloor plumbing lines, patch conc slab on grade; new high end plumbing fixtures and accessories; undermount sinks, polished stone floors, stone countertop. Counter to ceiling mirror + 1 full length mirror. Period light fixtures. Two stalls, two urinals, four lavs.Each water closet to be in a "room" with a louvered door. | 1 | ls
Room 104A
New work description
Walls: Plaster/painted. moderate soiling - clean 300 sf. 50 sf plaster repair (1 location) | 50 | sf
Ceiling: Plaster/painted. Moderate soiling - clean 150 sf. 10 sf plaster repair (1 location). | 10 | sf
Room 116
Add this to the current work scope for this room:
Dining room: Highly intricate molded plaster ceiling repair: floral relief work, cast from historic molds (Meadowbrook owns), including hand work to blend new with old. | 10 | SF | 550 | 5500
Paint for above (single color), including cleaning of adjacent smoke stained areas to permit paint match. (intricate cleaning work - likely toothbrushes and q-tips) | 40 | SF | 175 | 7000
Dining room: Remove loose flat plaster down to sound matl. Leave existing lath. Patch with plaster. | 20 | SF | 85.1806 | 1703.6117
Paint for above | 20 | SF | 4 | 80
Room 117 - Breakfast Nook
Add this to the current work scope for this room:
Walls - Miscellaneous minor plaster repair - small scattered areas in flat wall areas, + paint | 20 | SF | #DIV/0! | #DIV/0!
Breakfast Room: Carefully remove existing painted wall cloth; prep substrate, install new wall cloth; field paint - single color. | 20 | SF | 120 | 2400
Selective mural conservation | 10 | SF | 200 | 2000
Room 126/127 - Wilson Room
Upgrade lighting (new off-the-shelf fixtures, flexible controls) | 800 | sf
5 new display cabinets (custom, wood with glass, internally lit, high quality materials and finishes, approx 2' x 4 x 7 feet high.). | 5 | ea
Paint walls | 1056 | sf
Paint Ceiling | 800
Touch up stain on wood trim. Assume 6" wide profiled boards scattered locations | 50 | locations
Misc. minor flat plaster repair (minor crack repairs) | 50 | lf
Room 130 - Floral Room:
Room is 12' x 15'. New walk-in flower cooler with glass doors (approx 8' x 8'). New custom base cabinets, L-shaped in plan (12' x 10'), 42" H, 3' deep. High Pressure plastic laminate doors and shelves, solid surface countertop. New lighting (fluorescent, color corrected). New heavy duty sheet vinyl floor. Paint walls and ceiling. | 1 | ls
Room 214- Matilda's Room
Add this to the current work scope for this room:
Plaster cornice: Repair straight run plaster cornice approx 24" high: Carefully remove existing custom fabric adhered silk on cornice; remove and relace damaged finish plaster (assumed shallow repair - complete removal is not required). | 3 | LF | 1000 | 3000
Walls: carefully remove stretched silk wall fabric. Repair plaster finish (assumed superficial damage). | 30 | SF | 30 | 900
New Silk wall coverings over entire room: custom woven silk damask fabric to match existing EXACTLY in color and pattern, stretched over frame. It will be impossible to match existing in damaged area above due to differential fading, so whole room is indicated here. Also, New silk cornice cover: custom woven to match existing, and Cornice finishes: metallic gold paint | 1 | ALLOW | 25000 | 25000
Room 217 - English Room
Add this to the current work scope for this room:
Cornice: ornamental cornice: 12" deep straight run plaster cornice: Repair: remove damaged material; re mold to match existing | 30 | LF | 200 | 6000
Paint for above (single color) | 30 | SF | 8.3333 | 250
Ceiling: remove damaged plaster & mtl lath; Install new three coat plaster on mtl lath. | 150 | SF | 200 | 30000
Paint for above (entire ceiling) | 150 | SF | 8.3333 | 1250
Walls: remove damaged plaster (assume superficial damage, and lath and most of base coats are salvageable); repair finish coat with new plaster. | 25 | SF | 15 | 375
Paint for above - sponge finish - entire room | 375 | SF | 2.1167 | 793.75
The following should be listed under the heading "Room Renovations"
Stanchions, Signs
OU cost from vendor | 1 | ls | 8000
Kitchen Refrigerators
4 Existing tile lined custom refrigerators: 1 @ 5' x 15', 3@4' x 8'
Compressors, etc. are new - no work needed on them. | n/a
Remove existing white tile, cork backup, walls. Rebuild custom with new walls, stainless steel lining, at walls and ceilings, insulation, vapor barriers. Reconnect to existing compressors. New lighting. | 200 | sf
Restrooms for Tents
New freestanding restroom facility not connected to mansion Large facility. This number is from OU, obtained from an Architect. | 1 | ls | 480000
Kitchen for Tents
New freestanding Kitchen building not connected to mansion. Full kitchen. This number is from OU, obtained from an Architect. | 1 | ls | 259000
Kitchen Upgrades (in Mansion)
Existing 22 x 25 kitchen in house. Replace all appliances, hoods, etc. Commercial appliances. OU has estimate from kitchen specialists of $840,000 | 1 | ls | 840000
New second tent off Sun Porch | 1 | ls | 780000
Pad for above | 1 | ls | 200000
Upgrade existing tent | 1 | ls | 560000
Replace existing tent pad. | 1 | ls | 100000
Highly sophisticated tents, with elaborate interior finishes, floors. Costs for the 4 items above are from tent suppliers and are reliable.
The following should be a separate heading:
Allowances to Accommodate Wall/Ceiling Repairs to accommodate Steam piping replacement.
Allowance for wall channeling and repairs to accommodate steam piping removal and replacement. Assume 300 locations, each 10' long vertical removal/repairs. Of these, assume 50% are in standard painted plaster walls, 30% are in special painted walls (ragged or sponge paint over canvas), and 20% are in walls with special architectural finishes (Natural wood paneling, stretched silk)
Allowance for Ceiling channeling and repairs to accommodate steam piping removal and replacement. Assume 300 lf. Of that, assume that 70% is in standard painted plaster ceilings, and 30% is in plaster ceilings with special textured finishes between ornamental carved wood beams approx 10' o.c. Assume beams will stay in place and plaster strips will be removed between beams, and pipes will be removed and re-fed over beams.
Note on B95: Jack Edwartoski, PE: Changed by GJ
Note on D97: Jack Edwartoski, PE: Change by GJ
Note on E103: Jack Edwartoski, PE: Total is low because ofsmall scale and fussy work. I don't think we are going to get out of that room for less than 2000. Adjust unit cost accordingly
Note on E124: Jack Edwartoski, PE: Allowance agreed upon by GJ and JE

## NIC Room Breakdown (hidden)
Proj. No.: | 21868 |  |  |  | Date: | 2003-11-26 |  |  | Date: | 2003-11-26
Project Name: | #REF! |  |  |  | Classification: |  |  |  | Classification:
Project Location: | #REF! |  |  |  | Bid Date: | 2003-11-26 |  |  | Bid Date: | 2003-11-26
Estimate Type: | #REF! |  |  |  | Gross Area SF: | #REF! |  |  | Gross Area SF: | #REF!
ITEM |  | DESCRIPTION | QTY |  | U.P. | TOTALS | QTY |  | U.P. | TOTALS
A. Wilson Room
Project Quantity |  |  | 1 | LS | 6000 |  | 959.85 | SF | 11.4862
Wilson Room |  |  | 1 | LS | 6000
No Written Scope Provided |  |  | 1 | LS | 117000 | 6000
Wilson Room | [6 empty] | 959.85 | SF | 11.4862
Solid wood timbers, 6" x 6" to 8" x 8", hand distressed for rustic appearance, pegged joints: Remove timber, replace with new. See stucco repair and painting below | [6 empty] | 1080 | SF | 2.5 | 2700
Faux wood timber facings: full 2" x 8" (actual dimension), custom milled, hand distressed for rustic appearance, pegged joints. Remove existing; remove bird refuse behind; install new. See stucco repair and painting below | [6 empty] | 900 | SF | 6.75 | 6075
Wood soffits at item A.2: 5/4 x 10 wood boards. Remove existing, remove bird refuse behind; install new. See painting below | [6 empty] | 1 | EA | 2250 | 2250
Epoxy repairs: Remove existing rotted timber matl to sound wood; clean debris from behind, prep surfaces, rebuild missing material with epoxy putty, sculpt surface for rustic appearance; assume typical section is 8" x 8" | [6 empty] | 0 | SF | 2.5 | 0
Dutchman repairs: Remove existing rotted timber matl to sound wood; clean debris from behind, prep joint to be tight & uniform.carefully cut new dutchman to fit tightly; epoxy in place. Hand distress to match rustic appearance | [6 empty] | 0 | SF | 5 | 0
Miscellaneous wood repairs, caulking etc. related to above.
Painting
Stucco Repair
[5 empty] | A. Wilson Room | 6000 |  |  |  | 11025
B. Lower Level: Expand 3 Ex. Restrooms
Project Quantity |  |  | 1 | EA | 340000 |  | 1 | EA | 80
Existing Restrooms | [5 empty] | 340000
No Written Scope Provided |  |  | 1 | LS | 117000
Existing Restrooms
(NOTE: I changed this category to include all masonry work, and therefore deleted the "chimneys" item below | [6 empty] | 1 | SF | 80
Brick repointing - walls | [6 empty] | 1 | SF | 10 | 10
Brick repointing - chimneys | [6 empty] | 1 | SF | 10 | 10
Minor brick replacement - chimneys | [6 empty] | 1 | SF | 10 | 10
Brick Cleaning - General | [6 empty] | 1 | SF | 10 | 10
Brick Cleaning - Lime stains | [6 empty] | 1 | SF | 10 | 10
Brick Cleaning - Algae | [6 empty] | 1 | SF | 10 | 10
Stone Repointing: repointing and sealants at copings | [6 empty] | 1 | SF | 10 | 10
Miscellaneous stone repointing (around windows, etc.) | [6 empty] | 1 | SF | 10 | 10
[5 empty] | B. Lower Level: Expand 3 Ex. Restrooms | 340000 |  |  |  | 80
C. Lower Level: New Restroom
Project Quantity |  |  | 1 | LS | 136000 |  | 1 | LS | 20
New Restroom |  |  | 1 | EA | 136000 | 136000
No Written Scope Provided |  |  | 1 | LS | 117000
New Restroom | [6 empty] | 1 | LS | 20
NOTE: OU is getting quotes from George Frisch on this work, which will be much more reliable than our numbers, since they have familiarity with the work. Their number should be plugged in here | [6 empty] | 1 | SF | 10 | 10
Verify if Frisch's number includes cleaning | [6 empty] | 1 | SF | 10 | 10
[5 empty] | C. Lower Level: New Restroom | 136000 |  |  |  | 20
D. Floral Room.
Project Quantity |  |  | 35 | LOC | 542.8571 |  | 35 | LOC | 3.2571
Foundation & Structural Repairs: | [5 empty] | 19000
No Written Scope Provided |  |  | 1 | LS | 117000
Foundation & Structural Repairs: | [6 empty] | 35 | LOC | 3.2571
(Comment: there may be a groundwater issue based on what we saw in the boiler room (rising damp), and the "frog hole," suggesting a failure or blockage of the foundation drainage system.) | [6 empty] | 1 | LS | 4 | 4
Below grade foundation Drainage: Test/inspect underground foundation drainage system that roof leaders are connected to to ensure if they are free flowing and draining; rod out IF REQUIRED (some may be required) | [6 empty] | 1 | LF | 5 | 5
Area wells: Clean and inspect. Determine if they have drains; test/inspect to determine if functional. Clean/rod out IF REQUIRED ( some will likely be required) | [6 empty] | 1 | EA | 30 | 30
Repoint interior of foundation walls: brick walls: rake out, repoint. | [6 empty] | 1 | SF | 75 | 75
[5 empty] | D. Floral Room. | 19000 |  |  |  | 114
E. Carriage House, Loft, Garage
Project Quantity |  |  | 1 | LS | 0 |  | 75 | LOC | 0
Carriage House
No Written Scope Provided |  |  | 1 | LS | 117000 | 0
Carriage House | [6 empty] | 75 | LOC | 0
Not addressed
[5 empty] | E. Carriage House, Loft, Garage | 0 |  |  |  | 0
F. Floor Protection
Project Quantity |  |  | 1 | LS | 32000 |  | 1 | LS | 0
Floor Protection |  |  | 1 | LS | 32000
No Written Scope Provided |  |  | 1 | LS | 117000 | 32000
Cylinder Retainers | [6 empty] | 1 | LS | 0
Included with BRICK MASONRY, PARAPETS, COPING AND STONEWORK above. | [6 empty] | 0 | LS | 0 | 0
[5 empty] | F. Floor Protection | 32000 |  |  |  | 0
G. Stanchions, Signs
Project Quantity |  |  | 1 | LS | 8000 |  | 1 | EA | 70
Stanchions, Signs |  |  | 1 | LS | 8000 | 8000
No Written Scope Provided |  |  | 1 | LS | 117000
Stanchions, Signs | [6 empty] | 1 | EA | 70
Replace double doors to Loggia Terrace (these are the large arched wood framed windows/doors that are in the snack shop, which used to be an open terrace). Three options below: | Replace double doors to Loggia Terrace (these are the large arched wood framed windows/doors that are in the snack shop, which used to be an open terrace). Three options below: | Replace double doors to Loggia Terrace (these are the large arched wood framed windows/doors that are in the snack shop, which used to be an open terrace). Three options below: |  |  |  |  | 1 | EA | 10 | 10
Option One: Remove and Replace one pair of 3' -0" x 6'-8" wood french doors with new in existing frames; replace threshold with new bronze; miscellaneous wood repairs at fram and at other three arched opening infills. | Option One: Remove and Replace one pair of 3' -0" x 6'-8" wood french doors with new in existing frames; replace threshold with new bronze; miscellaneous wood repairs at fram and at other three arched opening infills. | Option One: Remove and Replace one pair of 3' -0" x 6'-8" wood french doors with new in existing frames; replace threshold with new bronze; miscellaneous wood repairs at fram and at other three arched opening infills. |  |  |  |  | 1 | EA | 10 | 10
Option Two: Remove existing full-opening wood window/door infills at three existing openings; replace with three pairs of new custom wood framed wood full opening arched doors 4' x 8' half arched leaves. Insul glazing | Option Two: Remove existing full-opening wood window/door infills at three existing openings; replace with three pairs of new custom wood framed wood full opening arched doors 4' x 8' half arched leaves. Insul glazing | Option Two: Remove existing full-opening wood window/door infills at three existing openings; replace with three pairs of new custom wood framed wood full opening arched doors 4' x 8' half arched leaves. Insul glazing |  |  |  |  | 1 | EA | 10 | 10
Option three: As Opt. 2 above, but steel framed Hopes/Crittall type doors. Insul glass | Option three: As Opt. 2 above, but steel framed Hopes/Crittall type doors. Insul glass | Option three: As Opt. 2 above, but steel framed Hopes/Crittall type doors. Insul glass |  |  |  |  | 1 | EA | 10 | 10
Restore all exterior doors/hardware: Assume 15 exterior doors Total. Typical assumed treatment at all doors: adjust hardware: lubricate, tighten screws, weatherstrip, Adjust/resecure threshold. | Restore all exterior doors/hardware: Assume 15 exterior doors Total. Typical assumed treatment at all doors: adjust hardware: lubricate, tighten screws, weatherstrip, Adjust/resecure threshold. | Restore all exterior doors/hardware: Assume 15 exterior doors Total. Typical assumed treatment at all doors: adjust hardware: lubricate, tighten screws, weatherstrip, Adjust/resecure threshold. |  |  |  |  | 1 | EA | 10 | 10
Additional work at 7 of the above 15 doors: refinish exterior surface (strip, sand, some minor reattachment of veneers clear/stain). | Additional work at 7 of the above 15 doors: refinish exterior surface (strip, sand, some minor reattachment of veneers clear/stain). | Additional work at 7 of the above 15 doors: refinish exterior surface (strip, sand, some minor reattachment of veneers clear/stain). |  |  |  |  | 1 | EA | 10 | 10
Additional work at 10 of the above 15 doors: replace screening (use bronze screen material); | Additional work at 10 of the above 15 doors: replace screening (use bronze screen material); | Additional work at 10 of the above 15 doors: replace screening (use bronze screen material); |  |  |  |  | 1 | EA | 10 | 10
[5 empty] | G. Stanchions, Signs | 8000 |  |  |  | 70
H. Kitchen Refrigerators
Project Quantity |  |  | 1 | LS | 130000 |  | 199.875 | SF | 0.20013
Refrigerators |  |  | 1 | LS | 130000 | 130000
No Written Scope Provided |  |  | 1 | LS | 117000
Refrigerators | [6 empty] | 199.875 | SF | 0.20013
Restore leaded Glass: OU has a number for this from their stained glass specialist. | Restore leaded Glass: OU has a number for this from their stained glass specialist. | Restore leaded Glass: OU has a number for this from their stained glass specialist. |  |  |  |  | 1 | EA | 10 | 10
Replace Screens (bronze screening material) at 250 out of 500 total windows | Replace Screens (bronze screening material) at 250 out of 500 total windows | Replace Screens (bronze screening material) at 250 out of 500 total windows |  |  |  |  | 1 | EA | 10 | 10
Repair at 250 of 500 total windows: windows are steel with custom operating hardware, including sliding arms, hold-open arms, etc. Assumed typical treatment:solvent/chemical removal of paint accumulation, dried lubricants, paint, etc. lubrication, some physical bending to restore full operation. Clean paint from frames, weatherstrip (?); repaint interior and exterior. | Repair at 250 of 500 total windows: windows are steel with custom operating hardware, including sliding arms, hold-open arms, etc. Assumed typical treatment:solvent/chemical removal of paint accumulation, dried lubricants, paint, etc. lubrication, some physical bending to restore full operation. Clean paint from frames, weatherstrip (?); repaint interior and exterior. | Repair at 250 of 500 total windows: windows are steel with custom operating hardware, including sliding arms, hold-open arms, etc. Assumed typical treatment:solvent/chemical removal of paint accumulation, dried lubricants, paint, etc. lubrication, some physical bending to restore full operation. Clean paint from frames, weatherstrip (?); repaint interior and exterior. |  |  |  |  | 1 | EA | 10 | 10
Clean rust from south facing monumental windows in rooms 101, 102; repaint. Assume 2" x 2 inch mullion | Clean rust from south facing monumental windows in rooms 101, 102; repaint. Assume 2" x 2 inch mullion | Clean rust from south facing monumental windows in rooms 101, 102; repaint. Assume 2" x 2 inch mullion |  |  |  |  | 1 | EA | 10 | 10
[5 empty] | H. Kitchen Refrigerators | 130000 |  |  |  | 40
I. Restroom for Tents
Project Quantity |  |  | 199.875 | SF | 2426.5166 |  | 199.875 | SF | 8.005
Tent Restroom |  |  | 199.875 | SF | 2426.5166 | 485000
No Written Scope Provided |  |  | 1 | LS | 117000
Tent Restroom | [6 empty] | 199.875 | SF | 8.005
[7 empty] | 2 | EA | 525 | 1050
[7 empty] | 1 | EA | 550 | 550
[5 empty] | I. Restroom for Tents | 485000 |  |  |  | 1600
J. Kitchen for Tents
Project Quantity |  |  | 199.875 | SF | 1295.8099 |  | 199.875 | SF | 0
Tent Kitchen | [5 empty] | 259000
No Written Scope Provided
Tent Kitchen
New Cedar shingle roof: Remove existing cedar roof, replace damaged sheathing (assume 50 sf) with new spaced 1x boards; replace rotted rafters (assume 2x10, total of 25 lf) treat attic for mold. Install new cedar roof over cedar breather; provide concealed ridge and soffit vents, terne coated stainless flashings. Note: Existing gutters and downspouts in vary good condition: no work except tightening up a few loose downspout joints.
[5 empty] | J. Kitchen for Tents | 259000 |  |  |  | 0
K. Kitchen Upgrades
Project Quantity |  |  | 1 | EA | 840000 |  | 1 | EA | 2250
Kitchen Upgrades |  |  | 1 | EA | 840000 | 840000
No Written Scope Provided |  |  | -1 | EA
|  |  | 1 | EA | 2250
Kitchen Upgrades | [6 empty] | 1 | 0 | 2250
[7 empty] | -1 | EA
[7 empty] | 1 | EA | 2250 | 2250
[5 empty] | K. Kitchen Upgrades | 840000 |  |  |  | 2250
L. New Second Tent off Sun Porch
Project Quantity |  |  | 106.7 | SF | 7310.2156 |  | 106.7 | SF | -2.0173
Sun Porch Tent |  |  | 106.7 | SF | 7310.2156 | 780000
No Written Scope Provided |  |  | -1 | EA
|  |  | -6 | SF | 8.75
Sun Porch Tent | [6 empty] | 106.7 | SF | -2.0173
Stair Hall: New molded plaster medallion in stair hall on repaired flat plaster (see below for flat work) (cost based on strand theater larger, less complex medallion. Cost reduced to take into account size & complexity of this item. | [6 empty] | -27 | SF | 5.75 | -155.25
Paint for above | [6 empty] | -6 | SF | 8.75 | -52.5
Dining room: Highly intricate molded plaster ceiling repair: floral relief work, cast from historic molds (Meadowbrook owns), including hand work to blend new with old.
Paint for above (single color), including cleaning of adjacent smoke stained areas to permit paint match. (intricate cleaning work - likely toothbrushes and q-tips)
English Room: ornamental cornice: 12" deep straight run plaster cornice: Repair: remove damaged material; re mold to match existing
Paint for above (single color)
Matilda's bedroom: Repair straight run plaster cornice approx 24" high: Carefully remove existing custom fabric adhered silk on cornice; remove and relace damaged finish plaster (assumed shallow repair - complete removal is not required). See below under "conservation items" for special finishes
Flat plaster ceiling repair:
Stair Hall: Remove damaged plaster & mtl lath, install new three-coat plaster on metal lath.paint
Paint for above
Dining room: Remove loose flat plaster down to sound matl. Leave existing lath. Patch with plaster.
Paint for above
Spanish room: remove damaged plaster & mtl lath; Install new three coat plaster on mtl lath.
Paint for above
English room: remove damaged plaster & mtl lath; Install new three coat plaster on mtl lath.
Paint for above (entire ceiling) | [6 empty] | -6 | LF | 1.25 | -7.5
[5 empty] | L. New Second Tent off Sun Porch | 780000 |  |  |  | -215.25
M. Pad for Tent off Sun Porch
Project Quantity |  |  | 106.7 | SF | 7310.2156 |  | 106.7 | SF | 178.0694
Sun Porch Tent Pad |  |  | 106.7 | SF | 7310.2156 | 780000
No Written Scope Provided |  |  | -1 | EA
Sun Porch Tent Pad | [6 empty] | 106.7 | SF | 178.0694
Spanish Room: Carefully remove damaged hand Stenciled adhered wall fabric (cut back to logical straight joint); carefully remove damaged plaster & mtl lath; Install new three coat plaster on mtl lath. (See below for new finish - hand stenciled wall cloth) | [6 empty] | -1 | EA |  | 19000
Stair Hall: Carefully remove damaged painted single color adhered wall fabric (cut back to logical straight joint); remove damaged plaster (assume superficial damage, and lath and most of base coats are salvageable); repair finish coat with new plaster. See below for new Wall fabric in stair hall
Breakfast Nook: miscellaneous minor plaster repair - small scattered areas in flat wall areas, + paint
English Room: remove damaged plaster (assume superficial damage, and lath and most of base coats are salvageable); repair finish coat with new plaster.
Paint for above - Sponge finish to match existing.
Paint for above - Add for entire room
Matilda's Bedroom: carefully remove stretched silk wall fabric. Repair plaster finish (assumed superficial damage). See "conservation items" below for special finish
Breakfast Room: Carefully remove existing painted wall cloth; prep substrate, install new wall cloth; field paint - single color.
Wall Cloth with Hand Stenciling in Spanish room
Wall Cloth in Stairway (walls); single color field painted
Wall Cloth in Breakfast Room - Single color field painted | [6 empty] | -1 | EA
Selective mural conservation | [6 empty] | -3 | EA
[7 empty] | -10 | LF
[7 empty] | -2 | EA
[5 empty] | M. Pad for Tent off Sun Porch | 780000 |  |  |  | 19000
N. Upgrade Existing Tend
Project Quantity |  |  | 24 | LF | 32500 |  | 24 | LF | 685.4167
Sun Porch Tent Pad |  |  | 24 | LF | 32500 | 780000
No Written Scope Provided |  |  | -1 | EA
Sun Porch Tent Pad | [6 empty] | 24 | LF | 685.4167
Miscellaneous repairs to stone floors throughout building. Assume minor, small, and scattered, but numerous, in a variety of stone types and sizes. Assume 50 repair areas of 4 sf or less ea. Scope: primarily regrout joints (no removal of stones or resetting), except assume 3 of the 50 areas where stone flooring needs to be removed and reset. assume some sealers required. Stone floor work generally rustic, wide joints, assume stones are approx 1.5" thk. | [6 empty] | -4 | EA |  | 13000
[7 empty] | -2 | EA
[7 empty] | 3 | EA | 550 | 1650
[7 empty] | 1 | EA | 1800 | 1800
[5 empty] | N. Upgrade Existing Tend | 780000 |  |  |  | 16450
O. Replace Existing Tent
Project Quantity |  |  | 190 | SF | 68.4211 |  | 190 | SF | 8.4211
Tile Work |  |  | 190 | SF | 68.4211
Repair Tile and re-grout |  |  | 2 | EA | 525 | 13000
Tile Work | [6 empty] | 190 | SF | 8.4211
Similar scope and severity to Stone floor work above. Difference is that tile work regrouting is finer work, with fragile and difficult to replace materials in some cases. | [6 empty] | 2 | EA | 525 | 1050
[7 empty] | 2 | EA | 275 | 550
[5 empty] | O. Replace Existing Tent | 13000 |  |  |  | 1600